## Read Me
AI Risk Repository
Mapped to ISO/IEC 42001:2023 — AI Management System (AIMS)
This workbook now contains 40 ready-made example risks covering every part of ISO/IEC 42001 (governance, data, bias, security, privacy, third-party, human oversight, life cycle, documentation, audits and more), plus 30 blank rows for your own company risks.
What is this file?
This workbook is a Risk Repository (Risk Register) for Artificial Intelligence (AI) systems. It follows the requirements of ISO/IEC 42001:2023, the international standard for AI Management Systems. Every risk in this file is linked to the correct clause of the standard (Clause 4–10) and, where relevant, to a control in Annex A.
How to use this workbook:
1. Go to the 'Risk Register' sheet. This is the main working sheet.
2. Each row is one risk. Example rows are already filled in (Risk ID starting with 'EX-') — use them as a guide, then replace them with your own company's real risks.
3. Yellow cells are the cells you are expected to fill in or edit. Formula cells (grey) calculate automatically - do not overwrite them.
4. Use the drop-down lists provided for Category, Clause Reference, Likelihood, Impact, Treatment Option and Status. This keeps the register consistent and audit-ready.
5. The 'Risk Score' and 'Risk Level' columns calculate automatically from Likelihood x Impact. The colour (green/yellow/orange/red) shows the risk level at a glance.
6. Use the 'Risk Criteria' sheet to understand how Likelihood and Impact are scored (1 to 5).
7. Use the 'Annex A Control Map' sheet as a quick reference for which ISO/IEC 42001 Annex A control topic applies to which type of risk.
8. Review and update this register at planned intervals (e.g. quarterly) as required by Clause 8.2 and 8.3 of ISO/IEC 42001, and whenever a new AI system, major change, or incident occurs.
Sheets in this workbook:
- Read Me : This page
- Risk Register : The main risk repository (one row = one risk)
- Risk Criteria : Likelihood / Impact scoring scale and Risk Level bands
- Annex A Control Map : Summary of ISO/IEC 42001 Annex A control topics for quick reference
- Clause Reference : Summary of ISO/IEC 42001 main clauses (Clause 4-10) for quick reference
Notes:
- This workbook is a working template built to help your company implement Clause 6.1 (Actions to address risks and opportunities) of ISO/IEC 42001. It is not a certified or official ISO document.
- Field names and scoring scales can be adjusted to match your organisation's existing risk management framework (see Clause 6.1.1 of ISO/IEC 42001), as long as the logic stays consistent.

## Risk Register
AI RISK REPOSITORY — Mapped to ISO/IEC 42001:2023 (with CIA Rating)
Company Name: [Enter Company Name] ¦ AI Management System Scope: [Enter Scope] ¦ Prepared by: [Name] ¦ Last Updated: [Date] ¦ CIA = Confidentiality, Integrity, Availability
Risk ID | Date Identified | AI System / Process Name | Risk Category | ISO/IEC 42001 Clause Ref. | Annex A Control Ref. | Risk Description (what could go wrong) | Risk Source / Cause | Potential Consequence | Confidentiality (C) | Integrity (I) | Availability (A) | Likelihood (1-5) | Impact (1-5) | Inherent Risk Score | Inherent Risk Level | Existing Controls | Risk Treatment Option | Treatment Actions / Additional Controls Needed | Risk Owner | Target Completion Date | Residual Likelihood | Residual Impact | Residual Risk Score | Residual Risk Level | Status | Last Review Date | Next Review Date | Notes
EX-001 | 2026-01-10 | Customer Support Chatbot | Data Quality | 6.1.2 | A.7.4 | Chatbot gives wrong or outdated answers because training data is not refreshed. | No scheduled data refresh process; poor data quality control. | Customer complaints, loss of trust, wrong information given to customers. | Low | Medium | Low | 3 | 3 | 9 | Medium | Manual spot-checks of chatbot answers by support team. | Reduce | Set up quarterly data quality review and automated freshness checks. | Head of Customer Support | 2026-03-31 | 2 | 3 | 6 | Medium | In Progress | 2026-01-10 | 2026-04-10 | Linked to A.4.3.
EX-002 | 2026-01-12 | Résumé Screening Model | Bias & Fairness | 6.1.4 | A.5.4 | Hiring AI may unfairly reject candidates from certain demographic groups due to biased training data. | Historical hiring data reflects past biased decisions. | Discrimination claims, legal exposure, reputational damage, unfair impact on individuals. | Medium | High | Low | 3 | 5 | 15 | High | None currently in place. | Reduce | Perform AI system impact assessment; add bias testing; add human review of rejections. | Head of HR / AI Governance Lead | 2026-02-28 | 2 | 4 | 8 | Medium | Open | 2026-01-12 | 2026-02-15 | High priority.
EX-003 | 2026-01-15 | Fraud Detection Model | Model Performance / Robustness | 8.2 | A.6.2.6 | Model accuracy drops over time due to changing transaction patterns (data drift), missing fraud cases. | No continuous performance monitoring in production. | Increased financial loss from undetected fraud; regulatory scrutiny. | Medium | High | Medium | 4 | 4 | 16 | Critical | Manual monthly performance report reviewed by data science team. | Reduce | Implement automated drift monitoring, alerting, and retraining triggers. | Data Science Lead | 2026-03-15 | 2 | 4 | 8 | Medium | In Progress | 2026-01-15 | 2026-04-15
EX-004 | 2026-01-18 | All AI Systems | Security | 6.1.2 | A.6.2.3 | AI model could be attacked through data poisoning or model inversion, exposing sensitive data or corrupting outputs. | Lack of AI-specific security controls beyond standard IT security. | Data breach, loss of model integrity, regulatory penalties, reputational harm. | High | High | Medium | 2 | 5 | 10 | High | Standard network and access security controls (non-AI specific). | Reduce | Conduct AI-specific threat assessment; add input validation and anomaly detection. | Chief Information Security Officer | 2026-04-30 | 2 | 4 | 8 | Medium | Open | 2026-01-18 | 2026-04-30 | Coordinate with ISMS team.
EX-005 | 2026-01-20 | Marketing Content Generator | Transparency & Explainability | 9.3 | A.8.2 | Customers are not told when marketing content (images/text) is generated by AI. | No disclosure policy for AI-generated content. | Loss of customer trust; possible non-compliance with AI disclosure laws. | Low | Low | Low | 3 | 3 | 9 | Medium | None currently in place. | Reduce | Add clear AI-generated content labelling; update customer documentation. | Marketing Director | 2026-03-01 | 1 | 2 | 2 | Low | Open | 2026-01-20 | 2026-03-01
EX-006 | 2026-01-22 | Vendor Analytics Tool | Third-Party / Supplier | 6.1.3 | A.10.3 | A third-party AI vendor may change or discontinue their model without notice, disrupting operations. | No formal AI supplier risk management process; no AI-specific contract clauses. | Service disruption, inability to meet customer commitments, hidden compliance gaps. | Medium | Medium | High | 2 | 3 | 6 | Medium | Standard vendor contract without AI-specific clauses. | Transfer | Add AI-specific clauses (change notice, documentation rights); maintain supplier risk log. | Procurement Manager | 2026-05-01 | 1 | 2 | 2 | Low | Open | 2026-01-22 | 2026-05-01
EX-007 | 2026-01-24 | AI Governance Programme | Governance / Roles | 5.3 | A.3.2 | No one is clearly accountable for AI risk decisions across the company. | AI roles and responsibilities not formally defined or communicated. | Slow or inconsistent decision-making; risks fall through the gaps; audit failure. | Low | Medium | Low | 3 | 4 | 12 | High | Informal ownership by IT department. | Reduce | Define and document AI roles (owner, risk lead, reviewers); communicate across company. | Chief Technology Officer | 2026-02-20 | 1 | 3 | 3 | Low | Open | 2026-01-24 | 2026-02-20
EX-008 | 2026-01-25 | All AI Systems | Governance / Roles | 5.2 | A.2.2 | Company has no documented AI policy, so employees use AI tools inconsistently and without guardrails. | AI adoption grew faster than governance; no formal policy written. | Inconsistent AI use, higher risk exposure, difficulty proving compliance to regulators/auditors. | Low | Medium | Low | 4 | 3 | 12 | High | Informal verbal guidance from management. | Reduce | Draft and approve a formal AI policy; publish and train staff on it. | Chief Technology Officer | 2026-02-10 | 1 | 3 | 3 | Low | In Progress | 2026-01-25 | 2026-02-10
EX-009 | 2026-01-26 | Internal Whistleblowing Channel | Governance / Roles | 5.3 | A.3.3 | Staff have no clear channel to report concerns about how an AI system is being used. | No dedicated AI concern reporting process; general complaint channel not well known. | Issues stay hidden until they become serious incidents; loss of employee trust. | Medium | Low | Low | 3 | 3 | 9 | Medium | General HR complaint line (not AI-specific). | Reduce | Set up a confidential AI concern reporting channel with defined response process. | Head of Compliance | 2026-03-10 | 1 | 2 | 2 | Low | Open | 2026-01-26 | 2026-03-10
EX-010 | 2026-01-28 | Credit Scoring Model | Data Resources | 6.1.2 | A.4.3 | Data resources (training/validation/test data) used for the credit model are not documented, so origin and quality are unclear. | No standard process to log data resources used per AI system. | Cannot prove data quality/compliance to regulators; difficult to investigate errors. | High | High | Low | 3 | 4 | 12 | High | Data stored in shared drive without formal documentation. | Reduce | Create a data resource register for each AI system (source, quality, retention). | Data Governance Lead | 2026-03-20 | 2 | 3 | 6 | Medium | Open | 2026-01-28 | 2026-03-20
EX-011 | 2026-01-29 | All AI Systems | Resource Management | 7.1 | A.4.6 | Not enough skilled staff (data scientists, AI risk reviewers) to safely run and monitor AI systems. | Rapid AI adoption without matching hiring/training plan. | Poor oversight, slower incident response, higher chance of undetected errors. | Low | Medium | Medium | 4 | 3 | 12 | High | Existing IT team handling AI tasks alongside other duties. | Reduce | Hire or train dedicated AI resources; document required competencies (Clause 7.2). | Chief Technology Officer | 2026-06-30 | 3 | 3 | 9 | Medium | Open | 2026-01-29 | 2026-06-30
EX-012 | 2026-01-30 | Document Summarisation Tool | Data Quality | 6.1.2 | A.7.6 | Poorly prepared/cleaned input data causes the summarisation tool to produce inaccurate summaries. | No defined data preparation/cleaning standard before feeding documents to the model. | Wrong summaries used in business decisions; wasted staff time correcting errors. | Medium | Medium | Low | 3 | 3 | 9 | Medium | Users manually check summaries occasionally. | Reduce | Define data preparation criteria and methods; document in data preparation SOP. | Data Science Lead | 2026-04-01 | 2 | 2 | 4 | Low | Open | 2026-01-30 | 2026-04-01
EX-013 | 2026-02-01 | Loan Approval Model | AI System Impact | 6.1.4 | A.5.2 | No formal impact assessment has been done to check how the loan model affects applicants, especially vulnerable groups. | AI system impact assessment process not yet established. | Unidentified harms to applicants; regulatory non-compliance; reputational risk. | Medium | High | Low | 3 | 5 | 15 | High | None currently in place. | Reduce | Establish and run a formal AI system impact assessment process before next model update. | AI Governance Lead | 2026-03-05 | 1 | 4 | 4 | Low | Open | 2026-02-01 | 2026-03-05 | Critical - regulatory deadline.
EX-014 | 2026-02-02 | Facial Recognition Access System | Societal Impact | 6.1.4 | A.5.5 | Use of facial recognition for building access could disproportionately misidentify certain groups, causing unfair denial of access. | Vendor model not tested for accuracy across different demographic groups. | Discrimination complaints, legal exposure, harm to affected individuals, reputational damage. | High | High | Medium | 2 | 5 | 10 | High | Standard vendor accuracy claims only, not independently verified. | Reduce | Request independent bias/accuracy testing from vendor; add manual override option. | Facilities & Security Manager | 2026-04-15 | 1 | 4 | 4 | Low | Open | 2026-02-02 | 2026-04-15
EX-015 | 2026-02-03 | All AI Systems | Environmental Impact | 4.1 | A.5.5 | High energy use from running and training large AI models is not tracked, so environmental impact is unknown. | No monitoring of AI-related compute/energy consumption. | Unmanaged carbon footprint; possible conflict with company sustainability goals; reporting gaps. | Low | Low | Low | 3 | 2 | 6 | Medium | None currently in place. | Accept | Track cloud compute usage/energy cost for AI workloads; review annually. | IT Operations Manager | 2026-07-01 | 2 | 2 | 4 | Low | Open | 2026-02-03 | 2026-07-01 | Low priority for now.
EX-016 | 2026-02-04 | Sales Forecasting Model | Model Performance / Robustness | 6.2 | A.6.2.4 | Sales forecast model was never formally tested against defined acceptance/evaluation criteria before go-live. | No verification and validation process defined for AI models before deployment. | Inaccurate forecasts leading to poor business planning and financial loss. | Low | Medium | Low | 3 | 3 | 9 | Medium | Informal review by the analyst who built the model. | Reduce | Define verification/validation criteria and release checklist for all new models. | Head of Analytics | 2026-03-25 | 1 | 2 | 2 | Low | Open | 2026-02-04 | 2026-03-25
EX-017 | 2026-02-05 | All AI Systems | Documentation | 7.5 | A.6.2.7 | Technical documentation for AI systems (design, data, limitations) is missing or outdated. | No standard documentation template or requirement enforced during development. | Difficult to audit, onboard new staff, or respond to regulator requests; knowledge loss when staff leave. | Medium | Medium | Low | 4 | 3 | 12 | High | Some code comments exist; no formal documentation. | Reduce | Create mandatory AI system technical documentation template; backfill for existing systems. | AI Governance Lead | 2026-05-15 | 2 | 2 | 4 | Low | Open | 2026-02-05 | 2026-05-15
EX-018 | 2026-02-06 | All AI Systems | Documentation | 6.2.8 | A.6.2.8 | AI systems in production do not keep event logs, so it is impossible to trace what happened during an incident. | Logging not enabled or configured for AI system outputs and events. | Cannot investigate incidents properly; weak accountability; possible regulatory non-compliance. | Medium | High | Low | 3 | 4 | 12 | High | Basic application logs exist but do not cover AI-specific events. | Reduce | Enable AI-specific event logging (inputs, outputs, anomalies) with defined retention period. | Chief Information Security Officer | 2026-04-01 | 1 | 3 | 3 | Low | Open | 2026-02-06 | 2026-04-01
EX-019 | 2026-02-07 | HR Chatbot | Privacy | 6.1.2 | A.7.2 | HR chatbot processes employee personal data without a clear data protection review, risking privacy violations. | AI project launched without involving the privacy/legal team. | Breach of data protection law, fines, loss of employee trust. | High | Medium | Low | 2 | 5 | 10 | High | Standard company data protection policy (not AI-specific). | Reduce | Run a privacy impact assessment; align with ISO/IEC 27701 privacy controls. | Data Protection Officer | 2026-03-12 | 1 | 4 | 4 | Low | Open | 2026-02-07 | 2026-03-12
EX-020 | 2026-02-08 | Predictive Maintenance Model | Data Provenance | 6.1.2 | A.7.5 | Origin of sensor data used to train the maintenance model is not tracked, so its reliability cannot be confirmed. | No data provenance recording process across data pipelines. | Cannot trust model outputs; difficult to detect tampered or low-quality data sources. | Low | High | Medium | 3 | 3 | 9 | Medium | None currently in place. | Reduce | Implement data provenance tracking (source, date, transformations) for all training data. | Data Engineering Lead | 2026-05-01 | 2 | 2 | 4 | Low | Open | 2026-02-08 | 2026-05-01
EX-021 | 2026-02-09 | All AI Systems | Human Oversight | A.9.3 | A.9.3 | AI system decisions are automatically applied without any human review, even for high-impact cases. | No human oversight checkpoints defined in the AI system design. | Wrong automated decisions go unnoticed; harm to affected individuals; limited ability to correct errors quickly. | Low | High | Low | 3 | 4 | 12 | High | None currently in place. | Reduce | Add mandatory human review step for high-impact decisions; define override authority. | AI Governance Lead | 2026-03-20 | 1 | 3 | 3 | Low | Open | 2026-02-09 | 2026-03-20
EX-022 | 2026-02-10 | Customer-Facing AI Systems | Information for Users | 7.4 | A.8.2 | Users of AI-powered products are not given instructions on how the system works or its limitations. | No user-facing documentation created for AI features. | Misuse of the system by customers; support tickets; loss of trust when the AI behaves unexpectedly. | Low | Low | Low | 3 | 2 | 6 | Medium | Basic FAQ page exists, not AI-specific. | Reduce | Create AI feature user guide covering purpose, limitations, and how to get help. | Product Manager | 2026-04-10 | 1 | 2 | 2 | Low | Open | 2026-02-10 | 2026-04-10
EX-023 | 2026-02-11 | All AI Systems | Incident Management | 10.2 | A.8.4 | No defined plan exists to communicate an AI-related incident (e.g. wrong output causing harm) to affected users. | AI incidents are not integrated into the company's existing incident response plan. | Delayed or inconsistent communication after an incident; regulatory and reputational risk. | Medium | Medium | Medium | 2 | 4 | 8 | Medium | General IT incident response plan (not AI-specific). | Reduce | Add an AI incident communication plan to the existing incident response procedure. | Head of Compliance | 2026-04-20 | 1 | 3 | 3 | Low | Open | 2026-02-11 | 2026-04-20
EX-024 | 2026-02-12 | Recommendation Engine | Model Performance / Robustness | 8.2 | A.6.2.6 | Recommendation engine performance has never been re-evaluated since launch two years ago, despite changing customer behaviour. | No planned interval for re-running AI risk assessments and performance checks. | Model gives increasingly irrelevant or poor recommendations, hurting sales and customer experience. | Low | Medium | Low | 4 | 2 | 8 | Medium | None currently in place. | Reduce | Schedule a fixed review interval (e.g. every 6 months) for model performance checks. | Head of Analytics | 2026-03-30 | 2 | 2 | 4 | Low | Open | 2026-02-12 | 2026-03-30
EX-025 | 2026-02-13 | All AI Systems | Legal & Regulatory | 4.1 | A.2.3 | Company is not tracking new or upcoming AI laws and regulations that could apply to its AI systems. | No formal process to monitor external legal/regulatory developments related to AI. | Non-compliance with new legal requirements; fines; forced last-minute changes to AI systems. | Low | Low | Low | 3 | 4 | 12 | High | Legal team occasionally reviews general regulations, not AI-specific. | Reduce | Assign responsibility for monitoring AI regulatory developments; review quarterly. | Head of Compliance | 2026-03-01 | 2 | 3 | 6 | Medium | Open | 2026-02-13 | 2026-03-01
EX-026 | 2026-02-14 | Employee Productivity Monitoring Tool | Privacy | 6.1.4 | A.5.4 | AI-based monitoring tool tracks employee activity in ways that may be seen as excessive surveillance, harming morale and trust. | Tool deployed without assessing impact on employee wellbeing and privacy expectations. | Loss of employee trust, possible legal claims, negative workplace culture impact. | High | Medium | Low | 3 | 3 | 9 | Medium | General HR privacy notice (not specific to AI monitoring). | Reduce | Run impact assessment on employee wellbeing; limit data collected; communicate transparently. | Head of HR | 2026-04-05 | 2 | 2 | 4 | Low | Open | 2026-02-14 | 2026-04-05
EX-027 | 2026-02-15 | All AI Systems | Third-Party / Supplier | 6.1.3 | A.10.2 | Unclear who is responsible (company vs. AI vendor) if a third-party AI component fails or causes harm. | Responsibilities not documented between the organisation, suppliers, and partners. | Delayed response to failures, disputes with vendors, unclear accountability to affected customers. | Medium | Medium | Medium | 2 | 4 | 8 | Medium | General service agreements without clear AI responsibility split. | Reduce | Document responsibility allocation across the AI system life cycle with each supplier. | Procurement Manager | 2026-05-10 | 1 | 3 | 3 | Low | Open | 2026-02-15 | 2026-05-10
EX-028 | 2026-02-16 | New Internal AI Tool Requests | AI System Life Cycle | 6.2.2 | A.6.2.2 | New AI system ideas are built without documenting requirements, business case, or success criteria first. | No intake/approval process before AI development starts. | Wasted resources, systems that do not meet business needs, higher risk of poorly designed AI. | Low | Medium | Low | 4 | 2 | 8 | Medium | Informal discussions before starting a project. | Reduce | Create an AI project intake form requiring documented requirements and approval before build. | Chief Technology Officer | 2026-03-15 | 2 | 2 | 4 | Low | Open | 2026-02-16 | 2026-03-15
EX-029 | 2026-02-17 | All AI Systems | AI System Life Cycle | 6.2.5 | A.6.2.5 | AI systems are deployed to production without a documented deployment plan or release checklist. | No formal 'go live' approval process for AI systems. | Systems go live with unresolved issues; harder to roll back if something goes wrong. | Medium | Medium | Medium | 3 | 3 | 9 | Medium | Informal sign-off by project lead. | Reduce | Create a deployment plan template with release criteria and required approvals. | AI Governance Lead | 2026-04-01 | 1 | 2 | 2 | Low | Open | 2026-02-17 | 2026-04-01
EX-030 | 2026-02-18 | All AI Systems | Competence | 7.2 | A.4.6 | Employees using AI tools have not received training on responsible AI use, data handling, or company AI policy. | No AI training programme established for staff. | Misuse of AI tools, accidental data leaks, non-compliance with policy due to lack of awareness. | Medium | Low | Low | 4 | 3 | 12 | High | General IT security awareness training (not AI-specific). | Reduce | Develop and roll out mandatory AI awareness and responsible-use training for all staff. | Head of HR / L&D | 2026-04-30 | 2 | 2 | 4 | Low | Open | 2026-02-18 | 2026-04-30
EX-031 | 2026-02-19 | AI Chat Assistant (external website) | Transparency & Explainability | A.9.3 | A.9.3 | Website chat assistant cannot explain why it gave a particular answer, making it hard to resolve customer disputes. | Model type chosen has low explainability and no explanation feature was added. | Customer disputes cannot be resolved fairly; regulatory risk in explainability-sensitive sectors. | Low | Medium | Low | 2 | 3 | 6 | Medium | None currently in place. | Reduce | Add simple explanation features (e.g. show source documents used) where feasible. | Product Manager | 2026-05-20 | 1 | 2 | 2 | Low | Open | 2026-02-19 | 2026-05-20
EX-032 | 2026-02-20 | All AI Systems | Internal Audit | 9.2 | A.3.2 | No internal audits have ever been performed on the company's AI systems or AI management practices. | AI management system is new; audit programme not yet planned. | Undetected gaps in AI governance; unprepared for external certification or regulatory review. | Low | Low | Low | 3 | 3 | 9 | Medium | None currently in place. | Reduce | Plan and schedule the first internal AI audit within the next two quarters. | Head of Compliance | 2026-06-01 | 2 | 2 | 4 | Low | Open | 2026-02-20 | 2026-06-01
EX-033 | 2026-02-21 | All AI Systems | Management Review | 9.3 | A.2.4 | Top management has never formally reviewed the performance and risks of the company's AI systems. | No management review meeting scheduled for the AI management system. | Leadership unaware of AI risk exposure; slow strategic response to emerging issues. | Low | Low | Low | 3 | 3 | 9 | Medium | AI risks discussed informally in general leadership meetings. | Reduce | Schedule a formal quarterly AI management review with top management. | Chief Technology Officer | 2026-03-31 | 1 | 2 | 2 | Low | Open | 2026-02-21 | 2026-03-31
EX-034 | 2026-02-22 | Insurance Claim Auto-Approval System | Bias & Fairness | 8.4 | A.5.4 | Automated claim approval system may be systematically approving/rejecting claims differently based on region or customer type. | No fairness testing performed across customer segments before or after launch. | Unfair treatment of certain customer groups; regulatory investigation; reputational damage. | Medium | High | Low | 3 | 4 | 12 | High | Basic approval rate reporting, not segmented by fairness criteria. | Reduce | Run fairness analysis across customer segments; adjust model or add manual review where needed. | Head of Claims / AI Governance Lead | 2026-04-25 | 1 | 3 | 3 | Low | Open | 2026-02-22 | 2026-04-25
EX-035 | 2026-02-23 | All AI Systems | Nonconformity & Corrective Action | 10.2 | A.3.3 | When an AI system fails or breaks a rule, there is no formal process to record it and fix the root cause. | Nonconformity and corrective action process not defined for AI-specific issues. | Same problems repeat; no evidence of improvement for auditors or regulators. | Low | Medium | Low | 3 | 3 | 9 | Medium | Issues are fixed informally without a formal record. | Reduce | Create a nonconformity log for AI issues with root cause analysis and corrective actions. | Head of Compliance | 2026-04-15 | 1 | 2 | 2 | Low | Open | 2026-02-23 | 2026-04-15
EX-036 | 2026-02-24 | Voice Assistant Product | Security | 8.2 | A.6.2.3 | Voice assistant could be tricked by crafted audio inputs (adversarial attack) into giving harmful or wrong responses. | No adversarial robustness testing performed on the voice model. | Harmful or embarrassing outputs; safety risk if assistant controls physical devices; brand damage. | Medium | High | Medium | 2 | 4 | 8 | Medium | Basic input format validation only. | Reduce | Conduct adversarial robustness testing; add output filtering for unsafe responses. | Product Security Lead | 2026-05-30 | 1 | 3 | 3 | Low | Open | 2026-02-24 | 2026-05-30
EX-037 | 2026-02-25 | All AI Systems | Change Management | 6.3 | A.6.2.6 | Changes to AI models (e.g. retraining, new versions) go live without a planned change control process. | No change management procedure adapted for AI model updates. | Unexpected behaviour changes after updates; harder to trace which version caused an issue. | Medium | High | Medium | 3 | 3 | 9 | Medium | Developers push updates directly with minimal review. | Reduce | Introduce a change control process for AI model updates, including testing and rollback plan. | Data Science Lead | 2026-04-10 | 1 | 2 | 2 | Low | Open | 2026-02-25 | 2026-04-10
EX-038 | 2026-02-26 | Public-facing Image Generation Feature | Legal & Regulatory | 4.1 | A.9.4 | AI image generation feature could be misused to create misleading or inappropriate content, breaching intended use. | No usage restrictions, filters, or monitoring for misuse of the feature. | Legal liability, reputational damage, platform misuse by bad actors. | Medium | Medium | Low | 3 | 4 | 12 | High | Basic content filter provided by the underlying AI vendor. | Reduce | Add usage policy, stronger content filtering, and monitoring for misuse patterns. | Product Manager | 2026-04-20 | 2 | 3 | 6 | Medium | Open | 2026-02-26 | 2026-04-20
EX-039 | 2026-02-27 | All AI Systems | Resource Management | 7.1 | A.4.5 | Computing resources (servers, cloud capacity) for AI systems are not tracked, risking outages during high demand. | No formal resource planning for AI system computing needs. | System downtime during peak use; poor customer experience; emergency costs to scale up. | Low | Low | High | 3 | 2 | 6 | Medium | Cloud auto-scaling enabled for some systems only. | Reduce | Document computing resource requirements per AI system; set up monitoring and alerts. | IT Operations Manager | 2026-05-05 | 1 | 2 | 2 | Low | Open | 2026-02-27 | 2026-05-05
EX-040 | 2026-02-28 | All AI Systems | Communication | 7.4 | A.8.5 | No plan defines what AI-related information must be shared with regulators, customers, or partners, and when. | Communication requirements for AI topics not documented. | Missed regulatory deadlines; inconsistent messaging; loss of stakeholder trust. | Low | Low | Low | 2 | 3 | 6 | Medium | Ad-hoc communication handled case by case. | Reduce | Define what, when, how, and with whom the company communicates on AI topics. | Head of Compliance | 2026-04-25 | 1 | 2 | 2 | Low | Open | 2026-02-28 | 2026-04-25

## Risk Criteria
Risk Scoring Criteria
Used in the Risk Register to calculate Risk Score = Likelihood x Impact
Likelihood Scale
Score | Rating | Description
1 | Rare | May occur only in exceptional circumstances (e.g. once every few years).
2 | Unlikely | Could occur at some point (e.g. once a year).
3 | Possible | Might occur occasionally (e.g. every few months).
4 | Likely | Will probably occur in most circumstances (e.g. monthly).
5 | Almost Certain | Expected to occur frequently or is already occurring (e.g. weekly or continuously).
Impact Scale
Score | Rating | Description (impact on people, business, legal or society)
1 | Negligible | Minimal or no impact to individuals, business operations, or compliance. No harm to people or society.
2 | Minor | Small, easily corrected impact. Limited effect on a few individuals or minor operational disruption.
3 | Moderate | Noticeable impact on individuals or business processes; may require corrective action and management attention.
4 | Major | Significant harm to individuals or groups, serious compliance/legal exposure, or major reputational/financial damage.
5 | Severe | Widespread or irreversible harm to individuals, groups, or society; safety impact; severe legal, financial or reputational damage.
Risk Level Bands (Risk Score = Likelihood x Impact)
Score Range | Risk Level | What it means
1 - 4 | Low | Acceptable. Monitor through normal operations.
5 - 9 | Medium | Manage with existing controls; assign an owner and monitor regularly.
10 - 15 | High | Needs a risk treatment plan and management approval per Clause 6.1.3.
16 - 25 | Critical | Urgent action required; escalate to top management immediately (Clause 5.1).
CIA Rating (Confidentiality, Integrity, Availability)
Used in the Risk Register to show which security property of the AI system a risk affects most, in line with information security good practice (see ISO/IEC 27001).
CIA Element | What it means | Example
Confidentiality (C) | Risk of sensitive data (personal data, business data, model details) being seen or accessed by people who should not see it. | Training data leak exposes customer personal information.
Integrity (I) | Risk of AI system data or outputs being changed, corrupted, or made inaccurate - by accident or on purpose. | Attacker feeds bad data to the model so it makes wrong decisions (data poisoning).
Availability (A) | Risk of the AI system or its data becoming unavailable or unusable when needed. | AI service goes down during peak business hours due to a server overload.
Rating Scale
Rating | Meaning
High | Serious damage if this CIA property is affected (e.g. major data breach, complete outage, corrupted decisions at scale).
Medium | Noticeable but manageable damage (e.g. limited data exposure, partial slowdown, some incorrect outputs).
Low | Little to no meaningful damage if this CIA property is affected.

## Annex A Control Map
ISO/IEC 42001 Annex A — Control Reference Map
Use this list to pick the correct Annex A control reference in the Risk Register.
Annex A Ref | Topic | Covers (typical risk areas)
A.2 | Policies related to AI | AI policy, alignment with other policies, policy review
A.3 | Internal organization | AI roles & responsibilities, reporting of concerns
A.4 | Resources for AI systems | Data, tooling, system/computing, and human resources
A.5 | Assessing impacts of AI systems | AI system impact assessment process and documentation; impact on individuals, groups and societies
A.6 | AI system life cycle | Objectives & processes for responsible development; requirements, design, verification, deployment, operation, monitoring, technical documentation, event logs
A.7 | Data for AI systems | Data management, acquisition, data quality, data provenance, data preparation
A.8 | Information for interested parties | User documentation, external reporting, incident communication, information for interested parties
A.9 | Use of AI systems | Processes and objectives for responsible use; intended use of the AI system
A.10 | Third-party and customer relationships | Allocating responsibilities, suppliers, customers

## Clause Reference
ISO/IEC 42001 — Main Clause Reference (Clause 4-10)
Use this list to pick the correct clause reference in the Risk Register.
Clause | Title
4.1 | Understanding the organization and its context
4.2 | Understanding needs and expectations of interested parties
4.3 | Determining the scope of the AI management system
5.1 | Leadership and commitment
5.2 | AI policy
5.3 | Roles, responsibilities and authorities
6.1.2 | AI risk assessment
6.1.3 | AI risk treatment
6.1.4 | AI system impact assessment
6.2 | AI objectives and planning
7.1 | Resources
7.2 | Competence
7.4 | Communication
7.5 | Documented information
8.1 | Operational planning and control
8.2 | AI risk assessment (operation)
8.3 | AI risk treatment (operation)
8.4 | AI system impact assessment (operation)
9.1 | Monitoring, measurement, analysis and evaluation
9.2 | Internal audit
9.3 | Management review
10.2 | Nonconformity and corrective action